## Not_Invoiced_Report
				DEFECT SUMMARY - AWB entry form

Module	Found Date	Release	Occurrence	Issue No	Issue description	Defect Severity	Defect Status	Bug Report (Y/N)	Test Data	Comments	Developer	Developer Comments			Severity	OPEN	RE-OPEN	ON - HOLD	CLOSED	FIXED	DEFERRED	NOT APPLICABLE	Count
Not_Invoice_Report		3	3	1	Issue 001: System should have facility to generate the report by filtering only the agency and date range. But Currently user not be able to generate report without selecting unbilled or uninvoiced options. / Refer the screenshot.Issue 001: System should have facility to generate the report by filtering only the agency and date range. But Currently user not be able to generate report without selecting unbilled or uninvoiced options. / Refer the screenshot.	H	NOT APPLICABLE			QA: as discussed remove the ALL option. / Remove the Detail summary grid from the report.QA: as discussed remove the ALL option. / Remove the Detail summary grid from the report.		Please create a new case instead of commenting on the old case and reopening. / The All option was removed a couple of releases ago.
Not_Invoice_Report		1	1	2	Issue 002: weight column is missing in the summary grid. / Refer the screenshot.Issue 002: weight column is missing in the summary grid. / Refer the screenshot.	H	CLOSED
Not_Invoice_Report		3	2	3	Issue 003 : Total AWB count and weight count should be displayed under the summary grid. Currently it will not. Refer the screenshot.	H	CLOSED
Not_Invoice_Report		3	2	4	Issue 004 : Bill status name(Express.CfgBillStatus Table) should be displayed in Error Type column. Not the Bill status code. Currently system suppose to display bill status code. Refer the screenshot.Issue 004 : Bill status name(Express.CfgBillStatus Table) should be displayed in Error Type column. Not the Bill status code. Currently system suppose to display bill status code. Refer the screenshot.	M	NOT APPLICABLE			QA: ON HOLD DUE TO ISSUE 1 AND 3		Whats in there is developed according to the SRS.
Not_Invoice_Report		3	2	5	Issue 005 : Unbilled : system does not displayed ALL the unbilled product details, when user select All the products in search criteria. Refer the screenshot. / Test data :Date range(2020.01.23/2020.01.24)-fedex-lk / Products / -Inbound Freight / -Outbound Freight / -Third party freight / -Pick up / -PODIssue 005 : Unbilled : system does not displayed ALL the unbilled product details, when user select All the products in search criteria. Refer the screenshot. / Test data :Date range(2020.01.23/2020.01.24)-fedex-lk / Products / -Inbound Freight / -Outbound Freight / -Third party freight / -Pick up / -POD	H	FIXED					Screenshot in the attachement. Check and let me know the issues in it, will rectify. / For the date you gave, the data is skewed and difficult to test. So, I did the testing on 21st.
Not_Invoice_Report		1	1	6	Issue 006: Unbilled - when user generate report product wise, system displayed same data set for the every product . Refer the screenshot / Test data : Date Range (2020.01.24/2020.01.24)-fedex-lk) / Issue 006: Unbilled - when user generate report product wise, system displayed same data set for the every product . Refer the screenshot / Test data : Date Range (2020.01.24/2020.01.24)-fedex-lk)	H	FIXED					Check the screenshot for Issue no 5
Not_Invoice_Report		1	1	7	Issue 007: when user click on report summary grid, it will move on to the another screen. Refer the screenshots	M	DEFERRED	Need clarification.
Not_Invoice_Report		1	1	8	Issue 008: data is not getting viewed according to the selected invoice type , eg: filter for 2020/01/28 , there are 2 AWBs for POD and Freight invoice , and filter for POD only , both the data will get updated in the report. Data : 112623460444 , 119774423680 . / same should be validated for outbound , pickup as well.Issue 008: data is not getting viewed according to the selected invoice type , eg: filter for 2020/01/28 , there are 2 AWBs for POD and Freight invoice , and filter for POD only , both the data will get updated in the report. Data : 112623460444 , 119774423680 . / same should be validated for outbound , pickup as well.	H	CLOSED
Not_Invoice_Report		2	2	9	Issue 009: in the given report the error description should get updated. When users filtered from the agency and date range only.	H	CLOSED
Not_Invoice_Report		2	1	10	Issue 010: align the lines of the summary grid without stricking the word. Check word 'weight'	L	CLOSED
Not_Invoice_Report		2	1	11	Issue 011: serivce type is not getting updated in the report, after the Shipper / consignee values service type should get updated. Pls update the description of the service type. (Consult leel)	H	CLOSED
Not_Invoice_Report		3	2	12	Issue 012: bottom of the report the print user and date should get updated , as given in the srs. (good if you can refer the SRS since the report formt is given in that document)	M	FIXED
Not_Invoice_Report		2	1	13	Issue 013: Bill status name should be --> error type.	L	CLOSED
Not_Invoice_Report		2	1	14	Issue 014: incorrect summary is getting updated for below filtering , Uninvoiced , Inbound Freight.	M	CLOSED
Not_Invoice_Report		2	1	15	Issue 015: consignee tag is not visible to the users in the report.	L	FIXED
Not_Invoice_Report		3	1	16	Issue 016: after generating a report for the selections then try to select entering agency and date range only. Will not work	M	NOT APPLICABLE					You can click the cancel button to start it over.
Not_Invoice_Report		3	1	17	Issue 017: incorrect AWB count is getting updated for below , / Filter from Uninovice - Agency : FedEx - LK --> Third party. Date range 2020 -01- 28 to 30	H	FIXED